PADHAANEWALA EDUTECH SERVICES

BENGALURU - 560100

PROJECT PLAN

Padhaanewala Education Technology Platform

padhaanewala.in

Version: 1.0

Date: September 2026

# 1. PROJECT OVERVIEW

## 1.1. Project Summary

Padhaanewala is a comprehensive education technology platform designed to help students discover colleges, search courses, compare institutions, find scholarships, take mock tests, and receive AI-powered guidance. The platform is database-driven, scalable, and includes a full admin panel, CRM system, and lead management infrastructure.

## 1.2. Project Objectives

Build a professional, scalable, database-driven education platform

Provide accurate college and course information to students

Generate and manage admission leads for Padhaanewala business

Implement AI-powered features (College Predictor, Education Assistant)

Ensure admin can manage all content without coding knowledge

Achieve strong SEO presence for organic traffic growth

## 1.3. Project Scope

IN SCOPE:

Student-facing website (Next.js)

College, Course, Scholarship, Exam databases

AI College Predictor with RAG

AI Education Assistant with RAG

Mock Test system

College Comparison tool

Student accounts and dashboards

Admission enquiry and lead management system

Admin panel with CMS capabilities

Counsellor dashboard with role-based access

SEO infrastructure and programmatic SEO

Analytics and reporting

Blog and content management

OUT OF SCOPE (Future phases):

Mobile application (planned for future)

Online payments (planned for future)

Premium memberships (planned for future)

Multilingual support (planned for future)

## 1.4. Key Stakeholders

| Role | Person | Responsibility |
| --- | --- | --- |
| Project Owner | Padhaanewala Founder | Approvals, Business decisions, Final sign-off |
| Project Manager | To be assigned | Planning, Coordination, Risk management |
| Backend Engineers | To be assigned | FastAPI development, Database, APIs |
| Frontend Engineers | To be assigned | Next.js development, UI, Components |
| AI/ML Engineer | To be assigned | RAG pipeline, Embeddings, AI features |
| DevOps Engineer | To be assigned | Deployment, CI/CD, Monitoring, Infrastructure |
| UI/UX Designer | To be assigned | Design systems, Wireframes, Prototypes |
| Content Team | To be assigned | College data entry, Course content, Scholarships |
| QA Engineers | To be assigned | Testing, Quality assurance, Bug tracking |

## 1.5. Project Success Criteria

Homepage works correctly and looks professional

College search returns accurate, filtered results

College and Course pages display complete information

Admin can edit content without modifying code

Enquiries reach admin panel and CRM immediately

Authentication works securely (JWT + OTP)

Mobile version works on all devices

SEO basics configured (sitemap, schema, clean URLs)

HTTPS enabled and functioning

Database backup automated and tested

Security testing completed without critical issues

All major APIs tested and working

Error handling works (no technical errors shown to users)

Analytics configured (Google Analytics)

Sitemap available at /sitemap.xml

Production deployment stable

# 2. PROJECT TIMELINE

## 2.1. High-Level Timeline

| Month | Phase | Key Deliverables |
| --- | --- | --- |
| Month 1 | Foundation | Project setup, Database design, Authentication |
| Month 2 | Core Features | College system, Course system |
| Month 3 | Content & Search | Scholarships, Exams, Search enhancement |
| Month 4 | Student Features | Student accounts, Reviews, Comparison |
| Month 5 | AI Features | RAG setup, AI Predictor, AI Assistant |
| Month 6 | Admin & CMS | Admin panel, Content management |
| Month 7 | Mock Tests | Question bank, Test engine |
| Month 8 | CRM & Leads | Lead management, Counsellor system |
| Month 9 | Testing & Launch | Testing, Deployment, Production launch |

## 2.2. Detailed Weekly Breakdown

### Month 1: Foundation (Weeks 1-4)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 1 | Project initialization, Next.js + FastAPI setup, Docker configuration | Working dev environment |
| Week 2 | CI/CD pipeline (GitHub Actions), Authentication system (JWT + OTP) | Dev + Staging environments |
| Week 3 | All 45+ database tables, Alembic migrations, pgvector extension | Complete database schema |
| Week 4 | Seed data, Environment variables, Basic API endpoints | Basic API working |

### Month 2: Core Features (Weeks 5-8)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 5 | College CRUD (Admin API), College pages (Frontend) | College management system |
| Week 6 | College search with filters, CSV import functionality | College import + search |
| Week 7 | College gallery upload, Image optimization pipeline | Gallery working |
| Week 8 | Course CRUD, Course pages, College-Course relationships, Fee structure | Course system complete |

### Month 3: Content & Search (Weeks 9-12)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 9 | Scholarship database + pages | Scholarship system |
| Week 10 | Exam database + pages, Deadline tracking | Exam system |
| Week 11 | Natural language search (basic), Advanced filter UI | Search enhancement |
| Week 12 | Search pagination, Suggestions/autocomplete | Full search working |

### Month 4: Student Features (Weeks 13-16)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 13 | Registration/Login (OTP + Email), Student dashboard | Student authentication |
| Week 14 | Saved colleges, Profile management | Student profile complete |
| Week 15 | Review submission + moderation | Review system |
| Week 16 | College comparison tool, FAQ system | Comparison complete |

### Month 5: AI Features (Weeks 17-20)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 17 | pgvector configuration, Embedding generation service | RAG foundation |
| Week 18 | document_embeddings table, Vector search API, Celery embedding task | RAG pipeline |
| Week 19 | AI College Predictor with RAG | Predictor working |
| Week 20 | AI Education Assistant with RAG, AI Comparison, Source citation | All AI features |

### Month 6: Admin & CMS (Weeks 21-24)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 21 | All 18 admin modules | Admin panel complete |
| Week 22 | Role-based access control, Media management | Access control |
| Week 23 | Blog system, FAQ management | CMS content |
| Week 24 | Banner management, SEO metadata management | Full CMS working |

### Month 7: Mock Tests (Weeks 25-28)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 25 | Question CRUD (Admin), Question import (CSV) | Question bank |
| Week 26 | Question categories/difficulty, Question validation | Question bank ready |
| Week 27 | Test creation (Admin), Test taking interface (Student) | Test engine |
| Week 28 | Timer + navigation, Submission + scoring, Results + analytics | Mock test complete |

### Month 8: CRM & Leads (Weeks 29-32)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 29 | Enquiry forms (all pages), Lead management (Admin) | Lead capture |
| Week 30 | Lead source tracking, UTM tracking | Lead attribution |
| Week 31 | Counsellor dashboard, Lead assignment | Counsellor system |
| Week 32 | Follow-up system, Notes system, Contact status | Full CRM complete |

### Month 9: Testing & Launch (Weeks 33-36)

| Week | Activities | Deliverable |
| --- | --- | --- |
| Week 33 | Unit tests, Integration tests, E2E tests (Playwright) | Test report |
| Week 34 | Security testing, Performance testing, Mobile testing | Quality assurance |
| Week 35 | Production server setup, DNS, SSL, CDN, Monitoring, Backup | Production ready |
| Week 36 | Launch checklist verification, Production launch | LAUNCHED |

# 3. RESOURCE PLAN

## 3.1. Team Requirements

| Role | Count | Commitment | Responsibilities |
| --- | --- | --- | --- |
| Backend Developer (Python/FastAPI) | 1-2 | Full-time | APIs, Database, Auth, AI integration |
| Frontend Developer (Next.js/React) | 1-2 | Full-time | UI, Pages, Components, Responsive |
| Database Designer | 1 | Part-time | Schema, Migrations, Optimization |
| AI/ML Engineer (RAG) | 1 | Part-time | Embeddings, Vector search, AI pipeline |
| DevOps Engineer | 1 | Part-time | Docker, CI/CD, Deployment, Monitoring |
| UI/UX Designer | 1 | Part-time | Design system, Wireframes, Prototypes |
| Content/Data Entry Team | 2-3 | Full-time (Month 2+) | College data, Course data, Scholarships |
| QA Engineer | 1 | Part-time (Month 8+) | Testing, Quality assurance |

## 3.2. Technology Requirements

Frontend: Next.js, React, TypeScript, Tailwind CSS

Backend: Python, FastAPI

Database: PostgreSQL with pgvector

Cache: Redis

Storage: AWS S3 / Cloudflare R2

Search: PostgreSQL full-text search (later OpenSearch)

AI: OpenAI API + RAG pipeline

Queue: Celery

Containerization: Docker

CI/CD: GitHub Actions

Monitoring: Sentry, Datadog

CDN: Cloudflare

## 3.3. Infrastructure Requirements

| Resource | Specification | Required By |
| --- | --- | --- |
| Development Server | 2 vCPU, 4GB RAM, 50GB SSD | Stage 1 (Month 1) |
| Staging Server | 2 vCPU, 4GB RAM, 50GB SSD | Stage 2 (Month 1) |
| Production Server (Min) | 4 vCPU, 8GB RAM, 100GB SSD | Stage 3 (Month 9) |
| Production Server (Rec) | 8 vCPU, 16GB RAM, 200GB SSD | Stage 3 (Month 9) |
| Object Storage | S3/R2 - min 50GB | Stage 1 (Month 1) |
| Domain | padhaanewala.in | Stage 1 (Month 1) |

# 4. BUDGET PLAN

## 4.1. Development Cost Estimate

Note: Development cost depends on team size, location, and engagement model. Estimates below are indicative.

| Item | Basis | Estimate |
| --- | --- | --- |
| Team (7-9 members) | Monthly | $8,000 - $15,000 |
| Infrastructure | Monthly | $160 - $400 |
| Third-party services | Monthly | $50 - $150 |
| Total Monthly (Development) |  | $8,200 - $15,550 |
| Development Duration | 9 months |  |
| Total Development Cost (Est.) |  | $74,000 - $140,000 |

## 4.2. Monthly Operating Cost (Post-Launch)

| Item | Purpose | Monthly Cost |
| --- | --- | --- |
| Cloud Server (4 vCPU, 8GB) | AWS/DigitalOcean | $40-80 |
| Cloudflare Pro | CDN + WAF | $20 |
| AWS S3 / R2 | Storage (100GB) | $5 |
| SendGrid | Email (1000/day) | $20 |
| MSG91 | SMS | $25 |
| OpenAI API | AI usage | $50-100 |
| Domain | padhaanewala.in | $1/month |
| Sentry | Error tracking | $0-26 |
| Monitoring | Uptime/Perf | $0-50 |
| Team Maintenance | Support | $2,000-5,000 |
| Total (Min) |  | $2,160 |
| Total (Recommended) |  | $5,350 |

## 4.3. Cost Control Measures

Phase-wise development - launch early with core features

Open source tools wherever possible

Optimize AI usage - cache common queries

Start with minimum infrastructure, scale as needed

Use free tiers for monitoring tools initially

# 5. RISK MANAGEMENT PLAN

## 5.1. Risk Identification and Mitigation

| Risk | Impact | Description | Mitigation |
| --- | --- | --- | --- |
| College Data Accuracy | High | Wrong fees/admission data harm trust | Data verification workflow, official sources, periodic re-verification, user feedback |
| AI Hallucination | High | AI invents college names/facts | RAG pipeline, source citations, strict guardrails, no-hallucination rules |
| Team Capacity | Medium | Solo developer cannot complete in 9 months | Hire required roles, phase-wise delivery, prioritize core features |
| Delayed Timeline | Medium | Features take longer than planned | Weekly sprint reviews, prioritization, scope management |
| Data Collection Bottleneck | High | 1000+ colleges data entry is slow | CSV import, data entry team, template-based entry, outsourcing if needed |
| Natural Language Search | Medium | Complex NLP conversion fails | Start with keyword matching, improve iteratively, use AI for parsing |
| Programmatic SEO Quality | Medium | Google penalizes thin content | Minimum content threshold, noindex thin pages, quality over quantity |
| Infrastructure Cost | Medium | Running costs exceed budget | Start minimal, scale gradually, optimize resource usage |
| Security Breach | High | Data leak or hack | Security from day 1, penetration testing, monitoring, audit logs |
| Third-party API Downtime | Low | OpenAI/SendGrid offline | Fallback providers, retry logic, error handling |
| Scope Creep | High | Client requests grow beyond original scope | Clear scope definition, change request process, milestone sign-offs |
| Server Failure | Medium | Production downtime | Replication, automated backups, monitoring alerts, disaster recovery plan |

## 5.2. Risk Response Strategies

AVOID: Clear scope, change management process

MITIGATE: Regular testing, monitoring, backups

TRANSFER: Use managed services (cloud, CDN)

ACCEPT: Low-impact risks with minimal cost to fix

# 6. COMMUNICATION PLAN

## 6.1. Communication Channels

| Channel | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Daily Standup | Daily | Development team | Progress, blockers, next steps |
| Weekly Status Report | Weekly (Monday) | PM to Project Owner | Progress, milestones, issues, next week plan |
| Sprint Review | Bi-weekly | All stakeholders | Demo completed work, feedback |
| Milestone Review | End of each month | Project Owner + PM | Phase completion, sign-off |
| Change Request | As needed | Team + Project Owner | Scope changes approval |
| Emergency Communication | Immediate | PM + Project Owner | Critical issues, production incidents |

## 6.2. Reporting Requirements

Weekly progress report to Project Owner

Monthly milestone sign-off document

Bug/issue tracker updated continuously

Risk register reviewed weekly

Budget tracking report monthly

# 7. QUALITY MANAGEMENT PLAN

## 7.1. Quality Standards

Code follows PEP 8 (Python) and standard JS/TS conventions

All APIs documented with FastAPI Swagger

Unit test coverage: minimum 70% for backend

Performance: API response <200ms for most endpoints

Accessibility: WCAG 2.1 AA compliance

Responsive: Works on 320px to 1440px+ screens

## 7.2. Quality Gates

| Quality Gate | When | Responsible | Pass Criteria |
| --- | --- | --- | --- |
| Code Review | Every PR | Peer reviewer | No critical issues |
| Unit Tests | Every build | CI Pipeline | All tests pass |
| Integration Tests | Each phase | QA Engineer | Core flows work |
| Performance Test | Month 8 | QA Engineer | Response times ok |
| Security Scan | Month 8-9 | Security specialist | No critical vulnerabilities |
| UAT | Month 9 | Project Owner + selected users | User acceptance signed |

# 8. CHANGE MANAGEMENT PLAN

## 8.1. Change Request Process

Step 1: Stakeholder submits change request

Step 2: PM assesses impact (time, cost, scope)

Step 3: PM presents impact analysis to Project Owner

Step 4: Project Owner approves/rejects

Step 5: If approved, update project plan and schedule

Step 6: Communicate change to affected team members

## 8.2. Change Categories

CRITICAL: Must-have, affects launch (approve immediately)

IMPORTANT: Should-have, defer if possible

MINOR: Nice-to-have, add to future phase

# 9. DATA COLLECTION & CONTENT PLAN

## 9.1. Data Sources

Official college websites

Government education portals

Regulatory authorities (NMC, AICTE, INC, etc.)

University websites

Verified institutional communication

Public data sources

## 9.2. Data Collection Strategy

| Content Type | Quantity | Timeline | Who | Source |
| --- | --- | --- | --- | --- |
| College Data | 500-1000 | Month 2-4 | Data entry team + CSV import | Official websites, govt sources |
| Course Data | 50-100 | Month 2 | Admin + content team | Regulatory authorities |
| Scholarship Data | 100-200 | Month 3 | Content team | Govt scholarships portal |
| Exam Data | 30-50 | Month 3 | Content team | Official exam websites |
| Mock Test Questions | 2000-5000 | Month 7 | Question creators + import | Subject experts |
| Blog Articles | 50-100 | Month 6+ | Content writers | Education research |
| College Images | Per college | Ongoing | Web scraping + submissions | College websites |

## 9.3. Data Quality Process

Every record has: data_source, verification_status, last_verified_date

Source must be one of: official website, govt source, regulatory authority, university, verified communication

Fees marked as 'approximate' when not guaranteed

Verification team reviews data periodically

User feedback loop for data corrections

# 10. DEPLOYMENT & LAUNCH PLAN

## 10.1. Environment Strategy

| Environment | URL | Update Frequency | Purpose |
| --- | --- | --- | --- |
| Development | localhost | Daily | Feature development |
| Staging | staging.padhaanewala.in | Test releases | QA, UAT, client demo |
| Production | padhaanewala.in | Final | Live users |

## 10.2. Deployment Pipeline

GitHub Actions CI/CD:

1. Developer pushes code to feature/* branch

2. CI runs linting + unit tests

3. Code review + merge to develop branch

4. Auto-deploy to staging environment

5. QA testing on staging

6. Merge to main branch

7. Auto-deploy to production (after approval)

## 10.3. Launch Strategy

Soft launch with core features (Month 8.5)

Invite selected beta users for feedback

Fix critical issues from beta

Full production launch (Month 9)

Post-launch monitoring for 48 hours

Prepare rollback plan if critical issues occur

# 11. PROJECT GOVERNANCE

## 11.1. Decision Authority

| Decision Type | Decision Maker | Scope |
| --- | --- | --- |
| Daily Decisions | Development team | Technical choices within scope |
| Sprint Decisions | PM | Task priorities, sprint scope |
| Phase Scope | PM + Project Owner | Feature prioritization, scope |
| Budget Decisions | Project Owner | Budget allocation, hiring |
| Architecture Changes | PM + Tech Lead | Material architecture deviations |
| Final Approval | Project Owner | Launch approval, contract |

## 11.2. Milestone Sign-off

| Milestone | Target Date | Success Criteria |
| --- | --- | --- |
| M1: Foundation Complete | End of Month 1 | Database schema, auth, environment |
| M2: Core Features Complete | End of Month 2 | Colleges, Courses, Search |
| M3: Content Complete | End of Month 3 | Scholarships, Exams, Search |
| M4: Student Features | End of Month 4 | Accounts, Reviews, Comparison |
| M5: AI Features | End of Month 5 | Predictor, Assistant |
| M6: Admin Complete | End of Month 6 | Admin, CMS |
| M7: Mock Tests | End of Month 7 | Test engine complete |
| M8: CRM Complete | End of Month 8 | Leads, Counsellors |
| M9: LAUNCH | End of Month 9 | Production launch |

# 12. POST-LAUNCH SUPPORT PLAN

## 12.1. Support Structure (First 90 Days)

| Period | Monitoring Level | Response Time |
| --- | --- | --- |
| Week 1-2 | 24/7 monitoring | Critical bug fixes within 4 hours |
| Week 3-4 | High priority monitoring | Bugs fixed within 24 hours |
| Month 2 | Normal priority | Bugs fixed within 48 hours |
| Month 3 | Maintenance mode | Scheduled updates |

## 12.2. Maintenance Plan

Weekly data verification updates

Monthly dependency updates

Quarterly security audits

Continuous SEO improvements

Content updates (blogs, scholarships, exams)

## 12.3. Post-Launch KPIs (First 3 Months)

| KPI | Target (3 months) |
| --- | --- |
| Website visitors | 10,000/month |
| College page views | 5,000/month |
| Course page views | 3,000/month |
| Enquiries/Leads | 500/month |
| Predictor usage | 1,000/month |
| Mock test attempts | 500/month |
| Student registrations | 1,000/month |
| Blog readers | 2,000/month |
| Google ranking (target keywords) | Top 20 |

# 13. APPROVALS

This Project Plan has been reviewed and approved by:

| Role | Signature | Date |
| --- | --- | --- |
| Padhaanewala Founder / Project Owner | ______________________ | Date: ____________ |
| Project Manager | ______________________ | Date: ____________ |
| Lead Backend Engineer | ______________________ | Date: ____________ |
| Lead Frontend Engineer | ______________________ | Date: ____________ |